Applicant submits Construction Plan Package & Fees into EPR. Agency review takes 21 calendar days (Section 5.0).

Applicant Resubmits in EPR within 60 days.

Applicant request a Pre-Submittal Meeting and submits Concept Plan and Fees into the Electronic Plan Review (EPR) System.  Agency review takes 21 calendar days (Section 4.0).

Staff Approval?

YES (Approval Good for 3 years)

Applicant Resubmits in EPR within 60 days.

Applicant submits Plat & Fees into the (EPR). Agency review takes 15 calendar days (Section 8.0)

Staff Conduct Site Pre-Construction Inspection & Conference (Section 12.1)

Staff apply Approval Stamps and issue Storm Water Management Permit

Note:  (Section _____) indicates the Section in the Administrative Manual where additional information can be obtained.

NO (staff comments in EPR)

Staff Approval?

NO (staff comments in EPR)

YES (Approval Good for 3 years)

Site Construction Begins & Staff Inspects for Compliance (Section 12.1)

Staff Approval?

Performance Bond Obtained If COs Needed Before BMPs Installed (Section 9.2)

NO

YES

Applicant Submits BMP As-Built into EPR & Engineer Certifies Compliance

(Sections 10.3 & 12.1)

Staff Conduct Final Inspection for Approval of As-Builts and BMP Construction

(Section 12.2)

Staff Approval?

Applicant Obtains Maintenance Bond for BMP (Section 9.3)

NO

YES

Final Project Approval & Release of COs (Section 11.4)

Long-Term Maintenance of BMPs (Section 7.3)

Applicant Records Final Plat, Maintenance Agreement & Provides digital copies for staff to upload into EPM (Section 8.2)

Applicant sets BMP pre-construction meeting with staff at least 48 hrs prior to starting BMP construction (Section 12.1)

(rev. April 2018)

Owner Requests Release of Maintenance Bond Two (2) Years after Project Approval, (Section 9.3)

Owner Commences Annual BMP Compliance Inspections (Section 12.1)

Applicant Resubmits in EPR within 60 days.